## QA Decisions
Round | Category | Question | Chosen Answer | Rationale | Alternative 1 | Alt 1 Description | Alternative 2 | Alt 2 Description | Fallback Priority | Branch
R1 | Scope | Keep all 3 experiments or focus depth? | All 3 experiments | Broader appeal for ML venues. Variety helps workshop/preprint. | Only 4.1+4.2 (physics) | Deeper analysis, better for physics venues | Only 4.2+4.3 (skip phase) | Avoids MC bug dependency | Low | hl_exp1
R1 | Infrastructure | Fix in-house MC or use external library? | Fix in-house MC code | Full control, reproducibility. Bug likely sign convention — tractable. | External lattice library | Guaranteed correct thermalization, adds credibility | Both: fix + cross-validate | Most rigorous but most time-consuming | Medium | hl_mc_fix
R1 | Strategy | Target venue? | arXiv preprint + package release | No deadline pressure. Establish priority. Submit to venue later. | Workshop paper first | Lower bar, faster turnaround, community feedback | Full conference (ICLR) | 8-10 pages, extensive ablations, 12-16 week timeline | High | hl_paper
R1 | Framing | How to frame zero-parameter layer? | Feature engineering layer (like FFT) | Non-learnable but universally used. Novelty is in WHAT features. | Add learnable fiber-aware pooling | Stronger ML story, hybrid module | Preprocessing + architecture paper | Learning happens downstream; layer provides inductive bias | Medium | hl_classical
R2 | Physics | 2D or 4D for topological charge? | 2D primary + 4D proof-of-concept | Code works in 2D. Small 4D demo shows scaling. | Stay 2D only | Simpler, vortex winding is well-defined | Extend to 4D fully | Rigorous instanton connection, 4-6 extra weeks | High | hl_exp2
R2 | Architecture | Handle axis-angle correlation in rotation exp? | Features only, no reconstruction | Avoids correlation problem entirely. | Accept as limitation | Honest negative result if factored denoising fails | Cross-attention base/fiber | Preserves correlations, adds complexity | Medium | hl_exp3
R2 | Release | Package polish level? | Full library: core + examples + docs | Sphinx, tutorials, CI. Package IS core contribution. | Minimal viable: core + tests | Enough for pip install. Ship fast. | Research code only | Clean imports, GitHub link, no pip packaging | High | hl_docs
R2 | Baselines | S² control baseline? | HopfLayer base-only ablation | Same arch, isolates fiber contribution. No external lib. | Full s2cnn spherical CNN | Proper spherical convolutions, strongest baseline | Both | Base-only as primary + s2cnn as external reference | Low | hl_exp1
R3 | Numerics | atan2 singularity handling? | Clipped atan2 gradient (STE) | Clamp to [-M, M] near singularity. Minimal code change. | eps-regularized atan2 | Current approach. Simple, works for forward pass. | Sigmoid-based smooth phase | Fully smooth but forward pass approximation | High | hl_classical
R3 | 4D Design | 4D extension approach? | Minimal: per-link HopfLayer + aggregate | Reuses existing code. Simple. | Full 4D: 4D plaquette winding | Physically correct, substantial new code | Slice-based: 2D slices of 4D | Middle ground, some 4D structure | Medium | hl_exp2
R3 | API | Provide inverse Hopf map? | Yes, exact reconstruction (S²+S¹→S³) | Enables encode-decode. FFT analogy: forward + inverse. | One-way extraction only | Not needed for proposed experiments | Provide but don't emphasize | Utility method, not paper contribution | Low | hl_classical
R3 | Parameters | Transition temperature handling? | User-tunable with principled defaults | Constructor param. Guidance: temp ≈ a/2. | Adaptive from data | Self-tuning, no user intervention, complicates batching | Make it learnable (nn.Parameter) | ONE learnable param. Breaks pure geometric framing. | Medium | hl_classical
R4 | Algebra | Octonion implementation? | Cayley-Dickson from quaternions | Reuses quaternion_multiply. Non-associativity handled by construction. | Explicit 8×8 multiplication table | Fano plane. Direct but brittle. | Abstract algebra library | Clean but heavy dependency, may not support autograd | Low | hl_quat
R4 | Physics | Phase transition model for 2D SU(2)? | SU(2)+adjoint Higgs (existing model) | 2D pure SU(2) has NO phase transition. Adjoint Higgs does. | 3D SU(2) pure gauge | Genuine deconfinement at β_c≈5.0. Requires 3D MC code. | 2D U(1) as simpler testbed | BKT transition. But Hopf map doesn't directly apply. | High | hl_exp1
R4 | Gradient | STE smooth function choice? | Clipped atan2 gradient | Use native atan2 grad, clamp to [-M, M]. M≈100 hyperparameter. | Sigmoid-based smooth phase | φ ≈ π·sigmoid(k·a₃/a₀). Fully smooth. | Detach fiber from gradient | .detach() on fiber output. Simplest possible. | High | hl_classical
R4 | Architecture | Downstream architecture strategy? | Same CNN backbone, task-specific heads | Fair comparison. 3-layer ConvNet. Only final head varies. | Task-specific architectures | Better per-task, harder to attribute to HopfLayer | Simple linear probes | Strongest evidence for representation quality | Medium | hl_exp1
R5 | Scope | Octonionic Hopf (S⁷→S¹⁵→S⁸)? | Defer to v2 | Non-associativity complications. Ship 3 fibrations first. | Standard Hopf invariant construction | Per-chart. Document chart-dependence. | Forward projection only, skip fiber | Fiber is S⁷ not S¹, no phase angle. | Low | hl_quat
R5 | Analysis | Finite-size scaling depth? | Validate data quality only | Confirm β_c and ν. Main result is HopfLayer comparison. | FSS as secondary contribution | Transition signals as order parameters. Novel finding. | Minimal: show phase separation exists | Plot observable vs β. No formal FSS. | Medium | hl_exp1
R5 | Compute | GPU resources? | Local RTX 4090 + cloud for 64×64 | Plenty for ≤32×32. ~60 runs total. | Cloud GPU only | A100/V100. Parallelize seeds. Costs money. | CPU only | Limits lattice sizes. MC doesn't need GPU. | High | hl_exp1
R6 | Narrative | Higher Hopf fibrations in paper? | Experiments on S³→S² only, Library Overview section for others | Readers see framework generalizes. Experiments focus on one case. | Small experiment per fibration | Toy experiments show implementations work. | Mention in conclusion only | Cleanest narrative but under-sells library. | Medium | hl_paper
R6 | Statistics | Seeds and significance tests? | 5 seeds + paired t-test | 60 total runs. Standard for preprint. Mean ± std. | 10 seeds + Wilcoxon | Non-parametric, 120 runs. Better for conference. | 3 seeds + CI only | Minimal. 95% CI via bootstrap. Fastest. | High | hl_exp1
R6 | Legal | License? | MIT | Most permissive. Maximum adoption. Standard for ML libraries. | Apache 2.0 | Patent grant. More corporate-friendly. | GPL v3 | Copyleft. Limits corporate adoption. | Low | hl_docs
R6 | Framing | Include project origin story? | Clean presentation, no origin story | Purpose-built GDL tool. Save failure story for Candidate 1. | Brief mention in Motivation | One paragraph. Honest without oversharing. | Full context in introduction | Unusual but compelling research journey narrative. | Medium | hl_paper
R6 | Title | Paper title? | hopf-layers: Differentiable Fiber Bundle Decompositions for GDL | Broader. Matches library name. Signals multiple fibrations. | Original: HopfLayer...on Gauge Fields | Specific, emphasizes gauge theory. | Fiber-Aware Neural Networks via the Hopf Fibrations | Conceptual, plural fibrations. | Low | hl_paper
R6 | Reconstruction | Reconstruction type? | Exact only, no learnable components | Deterministic formula. FFT analogy holds. | Exact + optional learnable residual | Compensate for downstream perturbations. | Learnable reconstruction network | MLP. Loses mathematical guarantee. | Medium | hl_classical
R6 | Ablation | Ablation depth? | 4 configs: raw, base-only, base+fiber, full | Clean ladder. 12 configs per experiment. | 2 configs: base-only vs full | Simplest test. Fast. | 6+ configs: cross-combinations | Full factorial. Most informative. | High | hl_exp1
R6 | Data | Lattice sizes? | Multiple: 8, 16, 32, 64 | Gold standard for lattice studies. FSS analysis. | 16 to 32 only | Standard, quick generation. 10K+ configs feasible. | Up to 64 | Stronger claims, 16x slower per config. | Medium | hl_exp1
R6 | Prediction | Rotation experiment prediction target? | Clean rotation matrix (9 values) | Standard. Frobenius norm or geodesic distance metric. | Euler angles (α, β, γ) | Simpler output but gimbal lock. | Axis-angle (axis + angle) | Parallels Hopf decomposition but singularity at angle=0. | Low | hl_exp3

## Fallback Matrix
Decision | Current Choice | Fallback Trigger | Fallback Action | Impact on Timeline
All 3 experiments | All 3 | Exp 4.3 shows no improvement | Drop 4.3, focus depth on 4.1+4.2 | Save 1-2 weeks
Fix in-house MC | Fix in-house | Bug intractable after 1 week | Switch to external library (openQCD) | Add 1 week for integration
arXiv + package | arXiv preprint | Results too strong for just preprint | Upgrade to ICLR/NeurIPS submission | Add 4-6 weeks for reviews
Full library release | Full docs+CI | Timeline pressure | Ship minimal viable (core+tests only) | Save 1-2 weeks
All 4 Hopf fibrations | Real+Complex+Quat | Quaternionic Hopf has numerical issues | Ship classical only, others as 'experimental' | Save 1 week
Multiple lattice sizes (FSS) | 8,16,32,64 | 64×64 too slow / cloud unavailable | Drop 64, FSS with 8,16,32 only | Save 2-3 days
4D proof-of-concept | Minimal 4D | Per-link aggregation doesn't correlate | Drop 4D, present 2D results only | Save 1 week
5 seeds per config | 5 seeds | Compute budget exceeded | 3 seeds + bootstrap CI | Save 40% compute
Clipped atan2 STE | STE | Gradient instability in practice | Fall back to eps-regularized atan2 | None
SU(2)+adjoint Higgs | Adjoint Higgs | Phase transition hard to locate | Switch to 3D SU(2) pure gauge | Add 1-2 weeks for 3D MC code
Same backbone across exp | Shared CNN | Shared backbone underperforms on all tasks | Allow task-specific tuning | Add 3-4 days
Exact reconstruction only | Exact inverse | Downstream tasks need approximate inverse | Add learnable residual correction | Add 2-3 days

## Project Structure
Path | Type | Purpose | Status
hopf-layers/ | dir | Project root | Created
pyproject.toml | file | Build system, metadata, dependencies, pytest config | TODO
README.md | file | Install, quick start, API overview | TODO
LICENSE | file | MIT License | TODO
.gitignore | file | Python, data, checkpoints exclusions | TODO
src/hopf_layers/ | dir | Main library source (src layout) | Created
__init__.py | file | Public API: HopfLayer, QuaternionHopf, RealHopf, etc. | TODO
quaternion.py | file | Quaternion algebra: normalize, multiply, conjugate, inverse, to/from SU(2) | TODO
classical.py | file | Classical Hopf: S¹→S³→S² layer + HopfOutput dataclass | TODO
real.py | file | Real Hopf: S⁰→S¹→S¹ decomposition | TODO
quaternionic.py | file | Quaternionic Hopf: S³→S⁷→S⁴ via Cayley-Dickson | TODO
transitions.py | file | Differentiable transition detection (tanh soft-threshold) | TODO
reconstruction.py | file | Exact inverse: (S², S¹) → S³ | TODO
utils.py | file | Shared utilities, clipped atan2 STE | TODO
tests/ | dir | pytest test suite | Created
test_quaternion.py | file | Quaternion algebra correctness | TODO
test_classical_hopf.py | file | S³ constraint, S² constraint, fiber range, equivariance | TODO
test_real_hopf.py | file | Real Hopf correctness | TODO
test_quaternionic_hopf.py | file | S⁷/S⁴ constraints, gradient flow | TODO
test_transitions.py | file | Winding detection: single vortex, pairs, anti-vortex | TODO
test_reconstruction.py | file | Round-trip: decompose → reconstruct = identity | TODO
test_gradient_flow.py | file | Backward pass through all operations, STE verification | TODO
examples/ | dir | Example scripts for users | Created
01_basic_usage.py | file | Minimal HopfLayer usage on random quaternions | TODO
02_lattice_gauge.py | file | Apply to SU(2) lattice gauge configuration | TODO
03_rotation_features.py | file | Rotation denoising feature extraction | TODO
docs/ | dir | Sphinx documentation | Created
conf.py | file | Sphinx configuration | TODO
index.rst | file | Documentation index | TODO
api/ | dir | Auto-generated API reference | Created
tutorials/ | dir | Tutorial pages | Created
experiments/ | dir | Paper experiment code | Created
exp1_phase_classification/ | dir | Experiment 4.1: SU(2) phase classification | Created
configs/ | dir | Experiment configs (beta values, lattice sizes, seeds) | Created
data/ | dir | Generated lattice configurations (.pt) | Created
models/ | dir | Trained model checkpoints | Created
results/ | dir | Metrics, plots, statistical tests | Created
run.py | file | Main experiment runner | TODO
exp2_topological_charge/ | dir | Experiment 4.2: topological charge | Created
(same substructure as exp1) |  |  | Created
exp3_rotation_denoising/ | dir | Experiment 4.3: rotation denoising | Created
(same substructure as exp1) |  |  | Created
baselines/ | dir | Shared baseline implementations | Created
backbone.py | file | Shared 3-layer CNN backbone | TODO
vanilla_cnn.py | file | Raw quaternion → CNN baseline | TODO
quaternion_cnn.py | file | Quaternion-aware CNN baseline | TODO
mc_generation/ | dir | Monte Carlo configuration generation | Created
su2_metropolis.py | file | Fixed SU(2) Metropolis MC | TODO
su2_adjoint_higgs.py | file | SU(2)+adjoint Higgs MC | TODO
paper/ | dir | LaTeX paper source | Created
main.tex | file | Paper manuscript | TODO
figures/ | dir | Publication-quality figures | Created
references.bib | file | BibTeX references (10+ papers) | TODO
notebooks/ | dir | Analysis and figure generation notebooks | Created
01_library_demo.ipynb | file | Library demonstration notebook | TODO
02_experiment_analysis.ipynb | file | Cross-experiment analysis | TODO
03_figure_generation.ipynb | file | Paper figure generation | TODO
QA/ | dir | Quality assurance and decision tracking | Created
decisions.xlsx | file | This file: all QA interview decisions | Created
create_decisions_xlsx.py | file | Script to regenerate this xlsx | Created

## Dependency Graph
Branch | Depends On | Blocks | Priority | Critical Path?
hl_pkg: Package Setup | (none — root) | hl_classical, hl_real, hl_quat | HIGH | YES
hl_mc_fix: MC Bug Fix | (none — root) | hl_exp1, hl_exp2 | HIGH | YES
hl_classical: Classical Hopf | hl_pkg | hl_quat, hl_exp1, hl_exp2, hl_exp3, hl_docs | HIGH | YES
hl_real: Real Hopf | hl_pkg | hl_docs | MEDIUM | No
hl_quat: Quaternionic Hopf | hl_pkg, hl_classical | hl_docs | MEDIUM | No
hl_exp1: Phase Classification | hl_classical, hl_mc_fix | hl_paper | HIGH | YES
hl_exp2: Topological Charge | hl_classical, hl_mc_fix | hl_paper | HIGH | YES
hl_exp3: Rotation Denoising | hl_classical | hl_paper | MEDIUM | No
hl_paper: Paper Writing | hl_exp1, hl_exp2, hl_exp3 | (none — terminal) | HIGH | YES
hl_docs: Documentation | hl_classical, hl_real, hl_quat | (none — terminal) | MEDIUM | No